## README
AGILE INTERNSHIP MANAGEMENT — ROLLING 10-WEEK MODEL
Mục đích | Quản lý nhóm sinh viên thực tập bắt đầu không đồng thời; mỗi sinh viên làm một project riêng thuộc Software Development, Data Analytics, AI/ML Research hoặc Software Testing.
Cách dùng nhanh | 1) Nhập sinh viên ở sheet Students. 2) Chỉ cần nhập Start Date; các mốc 10 tuần tự tính. 3) Cập nhật Weekly Check-in. 4) Ghi Sprint Review khi đến mốc. 5) Theo dõi Dashboard để ưu tiên các trường hợp At Risk / Off Track.
Quy ước màu chữ | Xanh dương = người dùng nhập; đen = công thức; xám = giá trị tĩnh / hướng dẫn.
Risk | GREEN = On Track; YELLOW = cần chú ý; RED = chậm/blocked. Có thể nhập Manual Risk trong Students; nếu để trống, file dùng Auto Risk dựa trên milestone, blocker và số ngày từ lần cập nhật gần nhất.
Timeline | Week 1: Onboarding; Weeks 2–3: Sprint 1; Weeks 4–5: Sprint 2; Weeks 6–7: Sprint 3; Weeks 8–9: Sprint 4; Week 10: Final Review.
Google Sheets | File sử dụng các hàm phổ biến (IF, TODAY, COUNTIF, INDEX/MATCH, MAXIFS...) để dễ import lên Google Sheets. Một số chart/format có thể hiển thị hơi khác sau khi import.
Lưu ý Agile | Không dùng % complete làm chỉ số chính. Ưu tiên Sprint Goal → Increment/Evidence → Blocker → Risk → Next Milestone.

## Dashboard
AGILE INTERNSHIP DASHBOARD
As of | 2026-08-28
Active Students |  |  | GREEN |  |  | YELLOW |  |  | RED
4 |  |  | 4 |  |  | 0 |  |  | 0
Student ID | Student Name | Track | Week | Stage | Next Milestone | Due Date | Days Left | Blockers | Risk | Last Check-in | Status | Project
SAMPLE01 | Nguyễn Văn A | Software Development | 2 | Sprint 1 | Sprint 1 Review | 2026-09-07 | 10 | 0 | GREEN | 2026-08-28 | Active | Web-based Internship Portal
SAMPLE02 | Trần Thị B | AI/ML Research | 0 | Not Started | Start | 2026-08-31 | 3 | 1 | GREEN | 2026-08-28 | Active | Network Intrusion Detection using ML
SAMPLE03 | Lê Văn C | Data Analytics | 0 | Not Started | Start | 2026-09-14 | 17 | 0 | GREEN |  | Active | Electricity Usage Analytics
SAMPLE04 | Phạm Thị D | Software Testing | 0 | Not Started | Start | 2026-09-28 | 31 | 0 | GREEN |  | Active | E-commerce Automation Testing
Software Development | 1 |  | GREEN | 4
Data Analytics | 1 |  | YELLOW | 0
AI/ML Research | 1 |  | RED | 0
Software Testing | 1

## Config
CONFIGURATION
Parameter | Value | Description
Internship Duration (weeks) | 10 | Tổng số tuần thực tập
Sprint Length (weeks) | 2 | Độ dài mỗi Sprint
Inactive Warning (days) | 4 | Không có cập nhật quá số ngày này → Yellow
Inactive Critical (days) | 7 | Không có cập nhật quá số ngày này → Red
Milestone Warning (days) | 2 | Còn <= số ngày này đến milestone và có blocker → Yellow

## Lists
REFERENCE LISTS
Track | Student Status | Risk | Backlog Status | Item Type | Priority | Sprint | Review Result
Software Development | Active | GREEN | Backlog | Feature | Must | Onboarding | Achieved
Data Analytics | Completed | YELLOW | Todo | Research | Should | Sprint 1 | Partially Achieved
AI/ML Research | On Hold | RED | In Progress | Experiment | Could | Sprint 2 | Not Achieved
Software Testing | Withdrawn |  | Review | Analysis |  | Sprint 3
|  |  | Done | Test |  | Sprint 4
|  |  | Blocked | Documentation |  | Final
Bug
Spike

## Students
STUDENT INTERNSHIP PORTFOLIO
Student ID | Student Name | Track | Project Title | Start Date | End Date | Current Week | Current Stage | Next Milestone | Next Milestone Date | Days to Milestone | Last Check-in | Days Since Update | Open Blockers | Auto Risk | Manual Risk | Overall Risk | Status | Supervisor Notes | Repository / Evidence Link
SAMPLE01 | Nguyễn Văn A | Software Development | Web-based Internship Portal | 2026-08-17 | 2026-10-26 | 2 | Sprint 1 | Sprint 1 Review | 2026-09-07 | 10 | 2026-08-28 | 0 | 0 | GREEN |  | GREEN | Active | SAMPLE – xóa hoặc thay bằng dữ liệu thật
SAMPLE02 | Trần Thị B | AI/ML Research | Network Intrusion Detection using ML | 2026-08-31 | 2026-11-09 | 0 | Not Started | Start | 2026-08-31 | 3 | 2026-08-28 | 0 | 1 | GREEN |  | GREEN | Active | SAMPLE – xóa hoặc thay bằng dữ liệu thật
SAMPLE03 | Lê Văn C | Data Analytics | Electricity Usage Analytics | 2026-09-14 | 2026-11-23 | 0 | Not Started | Start | 2026-09-14 | 17 |  |  | 0 | GREEN |  | GREEN | Active | SAMPLE – xóa hoặc thay bằng dữ liệu thật
SAMPLE04 | Phạm Thị D | Software Testing | E-commerce Automation Testing | 2026-09-28 | 2026-12-07 | 0 | Not Started | Start | 2026-09-28 | 31 |  |  | 0 | GREEN |  | GREEN | Active | SAMPLE – xóa hoặc thay bằng dữ liệu thật
Formulas:
End Date = IF([Student ID]="","",[Start Date]+Config!$B4*7)
Current Week = IF([Student ID]="","",MAX(0,MIN(Config!$B4,INT((TODAY()-[Start Date])/7)+1)))
Current Stage = IF([Student ID]="","",IF(TODAY()<[Start Date],"Not Started",IF(TODAY()>[End Date],"Completed",IF([Current Week]=1,"Onboarding",IF([Current Week]<=3,"Sprint 1",IF([Current Week]<=5,"Sprint 2",IF([Current Week]<=7,"Sprint 3",IF([Current Week]<=9,"Sprint 4","Final"))))))))
Next Milestone = IF([Student ID]="","",IF(TODAY()<[Start Date],"Start",IF(TODAY()<=[Start Date]+7,"Charter Approved",IF(TODAY()<=[Start Date]+21,"Sprint 1 Review",IF(TODAY()<=[Start Date]+35,"Sprint 2 Review",IF(TODAY()<=[Start Date]+49,"Sprint 3 Review",IF(TODAY()<=[Start Date]+63,"Sprint 4 Review","Final Review")))))))
Next Milestone Date = IF([Student ID]="","",IF(TODAY()<[Start Date],[Start Date],IF(TODAY()<=[Start Date]+7,[Start Date]+7,IF(TODAY()<=[Start Date]+21,[Start Date]+21,IF(TODAY()<=[Start Date]+35,[Start Date]+35,IF(TODAY()<=[Start Date]+49,[Start Date]+49,IF(TODAY()<=[Start Date]+63,[Start Date]+63,[Start Date]+70)))))))
Days to Milestone = IF([Student ID]="","",[Next Milestone Date]-TODAY())
Last Check-in = IF([Student ID]="","",IFERROR(LOOKUP(2,1/('Weekly Check-in'!$B4:B1003=[Student ID]),'Weekly Check-in'!$A4:A1003),""))
Days Since Update = IF([Student ID]="","",IF([Last Check-in]="","",TODAY()-[Last Check-in]))
Auto Risk = IF([Student ID]="","",IF(OR([Status]="Completed",[Status]="Withdrawn",TODAY()<[Start Date]),"GREEN",IF([Last Check-in]="","YELLOW",IF([Days Since Update]>=Config!$B7,"RED",IF(OR([Days Since Update]>=Config!$B6,AND([Days to Milestone]<=Config!$B8,[Open Blockers]>0)),"YELLOW",IF([Open Blockers]>0,"YELLOW","GREEN"))))))

## Weekly Check-in
WEEKLY CHECK-IN — DONE / NEXT / BLOCKER / EVIDENCE
Check-in Date | Student ID | Student Name | Current Stage | Current Goal | DONE since last update | NEXT | BLOCKER | EVIDENCE / Link | Risk Self-Assessment | Mentor Action | Notes
2026-08-28 | SAMPLE01 | Nguyễn Văn A | Sprint 1 | Implement authentication | Database schema + login API | Complete dashboard core flow |  | https://github.com/example/sample01 | GREEN | Review API security
2026-08-28 | SAMPLE02 | Trần Thị B | Not Started | Establish baseline | Prepared dataset and RF baseline | Evaluate XGBoost | Class imbalance | experiment-log/sample02 | YELLOW | Review sampling strategy

## Backlog
UNIFIED PRODUCT / RESEARCH BACKLOG
Student ID | Item ID | Sprint/Stage | Item Type | Title | Description | Acceptance Criteria | Priority | Estimate | Status | Evidence Link | Last Updated | Notes

## Sprint Reviews
SPRINT REVIEW & RETROSPECTIVE LOG
Review Date | Student ID | Student Name | Sprint | Sprint Goal | Goal Result | Increment / Deliverable | Evidence Link | Technical Findings | KEEP | PROBLEM | TRY | Backlog Changes | Mentor Feedback | Score (0-10) | Next Review Date

## Track Guide
TRACK-SPECIFIC SPRINT OUTCOMES & DEFINITION OF DONE
Track | Stage | Primary Focus | Expected Increment | Definition of Done / Evidence | Typical Backlog Types | Suggested Metrics
Software Development | Sprint 1 | Requirements + Architecture + Prototype | Runnable skeleton / MVP | Code pushed; build/run succeeds; acceptance criteria met; basic tests; demoable | Feature, Spike, Bug | Working features, defects, test pass rate
Software Development | Sprint 2 | Core Features | Core workflow works end-to-end | Same DoD + integrated core function | Feature, Bug, Test | Core scenario completion
Software Development | Sprint 3 | Integration + Quality | Integrated system | Integration tests; error handling; no critical known bug | Feature, Test, Bug | Defect trend, integration success
Software Development | Sprint 4 | Release + Deployment | Release candidate | Deployable; documentation; regression passed | Test, Documentation, Bug | Release readiness
Data Analytics | Sprint 1 | Problem + Data Understanding + EDA | Dataset, data dictionary, EDA | Question defined; data documented; EDA reproducible; findings evidenced | Analysis, Research | Data completeness, EDA findings
Data Analytics | Sprint 2 | Data Processing | Clean data + reproducible pipeline | Cleaning documented; pipeline reproducible; quality checks | Analysis, Documentation | Missingness, data quality
Data Analytics | Sprint 3 | Analysis | Validated insights | Method appropriate; visualization; evidence; limitations | Analysis, Research | Statistical/analytical evidence
Data Analytics | Sprint 4 | Communication | Dashboard/report + recommendations | Findings traceable to evidence; report/dashboard usable | Analysis, Documentation | Insight quality, usability
AI/ML Research | Sprint 1 | Literature + Dataset + Baseline | Reproducible baseline | Dataset/version logged; baseline code; metrics; experiment log | Research, Experiment | Baseline metrics
AI/ML Research | Sprint 2 | Proposed Method | First experiments | Hypothesis; configuration; reproducible code; results recorded | Experiment, Research | Metric vs baseline
AI/ML Research | Sprint 3 | Comparative Experiments | Comparison + ablation/validation | Appropriate metrics; repeated/controlled experiments; interpretation | Experiment | F1/AUC/etc., variance
AI/ML Research | Sprint 4 | Validation + Report | Final results + limitations | Final experiment set; comparison; negative results documented; reproducibility | Experiment, Documentation | Generalization, reproducibility
Software Testing | Sprint 1 | System Understanding + Risk | Test strategy | Scope, risks, scenarios, environment documented | Test, Research | Risk coverage
Software Testing | Sprint 2 | Test Design | Prioritized test cases | Expected result; traceability; critical flows covered | Test | Requirement/risk coverage
Software Testing | Sprint 3 | Automation | Automated test suite | Executable; results recorded; defects linked; code in Git | Test, Bug | Automation rate, pass rate
Software Testing | Sprint 4 | Regression + Reporting | Final QA report | Regression executed; evidence; defect summary; recommendations | Test, Documentation, Bug | Defect severity, regression pass rate

## Milestone Schedule
MILESTONE SCHEDULE — AUTO-GENERATED FROM START DATE
Student ID | Student Name | Start Date | Charter Approved | Sprint 1 Review | Sprint 2 Review | Sprint 3 Review | Sprint 4 Review | Final Review | End Date
SAMPLE01 | Nguyễn Văn A | 2026-08-17 | 2026-08-24 | 2026-09-07 | 2026-09-21 | 2026-10-05 | 2026-10-19 | 2026-10-26 | 2026-10-26
SAMPLE02 | Trần Thị B | 2026-08-31 | 2026-09-07 | 2026-09-21 | 2026-10-05 | 2026-10-19 | 2026-11-02 | 2026-11-09 | 2026-11-09
SAMPLE03 | Lê Văn C | 2026-09-14 | 2026-09-21 | 2026-10-05 | 2026-10-19 | 2026-11-02 | 2026-11-16 | 2026-11-23 | 2026-11-23
SAMPLE04 | Phạm Thị D | 2026-09-28 | 2026-10-05 | 2026-10-19 | 2026-11-02 | 2026-11-16 | 2026-11-30 | 2026-12-07 | 2026-12-07